## Stories
Stories
Story ID | Story Description | Comments
1 | As a player, I want to be able to compete against other players so I can have fun and display my abilities.
2 | As a player, I want to be able to compete against a computer so I can play when I have no other people to play against.
3 | As a player, I want to have different options for actions to take when battling so that I do not get bored with the game.
4 | As a player, I want to be able to perform a special attack so that I can use an ability that uses mana.
5 | As a player, I want to be able to use dice so that I will find the game more interesting.
6 | As a player, I want to be able to view the result of dice rolls so that I know how the results of attacks are computed.
7 | As a player, I want to be able to view my current score so I can see how well I am doing during a battle.
8 | As a player, I want to be able to exit during a battle in case I suddenly have to stop playing.
9 | As a player, I want to be able to log in so that my stats are not mixed up with other players' stats.
10 | As a player, I want to be able to view past statistics so that I can compare them to current stats and compete against them.
11 | As a player, I want to be able to navigate to different pages with a click so that I can easily access the game's features.
12 | As a player, I want to be able to see a nice user interface so that it is more of a pleasure to play the game.
13 | As a player, I want to have a user guide so I know how to use the game.

## Tasks
Tasks
Task ID | Task Name | Sprint ID | Story ID | Status | Expected Workload | Priority Level | Expected Duration | Comments
1 | User Stories | 1 |  | Completed | 1 | 1
2 | Use Case Diagram | 1 |  | Completed | 1 | 1
3 | Class Diagram | 1 |  | Completed | 1 | 1
4 | Sequence Diagram | 1 |  | Completed | 1 | 2
5 | GUI Design | 1 |  | Completed | 1 | 2
6 | Feature Backlog | 1 |  | Completed | 1 | 1
7 | Title Page GUI | 2 |  | In Progress | 1 | 3
8 | Game Description Page GUI | 2 |  | Not Started | 1 | 3
9 | Simple Battle Page GUI | 2 |  | Not Started | 3 | 1
10 | Usernames Stored and Retrieved from Database | 2 |  | Not Started | 3 | 1
11 | User Vs User Mode | 2 |  | Not Started | 2 | 1
12 | User Can Attack and Heal | 2 |  | Not Started | 1 | 1
13 | HP and Food Increase/Decrease | 2 |  | Not Started | 1 | 2
14 | View Score for Current Session | 2 |  | Not Started | 2 | 2
15 | Dice Roll Animation | 2 |  | Not Started | 2 | 2
16 | Display Result of Dice Roll and Computation | 2 |  | Not Started | 2 | 2
17 | Save Current Stats to File | 2 |  | Not Started | 1 | 3
18 | User Guide | 2 |  | Not Started | 1 | 1
19 | Full Battle Page GUI | 3 |  | Not Started | 3 | 5
20 | User Can Battle Computer | 3 |  | Not Started | 3 | 5
21 | View Past Statistics | 3 |  | Not Started | 3 | 5
22 | View All Statistics | 3 |  | Not Started | 2 | 5
23 | User Can Special Attack | 3 |  | Not Started | 2 | 5
24 | MP Increase/Decrease | 3 |  | Not Started | 1 | 5
25 | User Can Save and Load Stats to and from Database | 3 |  | Not Started | 1 | 5
26 | User Can Exit With Data Saved | 3 |  | Not Started | 1 | 5
27 | Stats Page GUI | 3 |  | Not Started | 3 | 5
28 | Single Player/Duel Page GUI | 3 |  | Not Started | 2 | 5
29 | Player Name for Stats Page GUI | 3 |  | Not Started | 2 | 5

## Sprints
Sprints
Sprint ID | Sprint Deadline | Sprint Description
1 | 2016-04-01 | Have user stories, use cases diagram, and documentation completed and committed to Github
2 | 2016-04-15 | Have at least half of the tasks completed, documentation updated
3 | 2016-04-29 | Have everything completed, documentation updated