## Stories
Stories
Story ID | Story Description | Comments
1 | As a player, I want to be able to compete against other players so I can have fun and display my abilities.
2 | As a player, I want to be able to compete against a computer so I can play when I have no other people to play against.
3 | As a player, I want to have different options for actions (attack, eat, SP attack) to take when battling so that I do not get bored with the game.
4 | As a player, I want to be able to perform a special attack so that I can use an ability that uses mana.
5 | As a player, I want to be able to use dice so that I will find the game more interesting.
6 | As a player, I want to be able to view the result of dice rolls so that I know how the results of attacks are computed.
7 | As a player, I want to be able to view my current score so I can see how well I am doing during a battle.
8 | As a player, I want to be able to exit during a battle in case I suddenly have to stop playing.
9 | As a player, I want to be able to save statistics from battles so that I can view them when I want to.
10 | As a player, I want to be able to view my player status (HP, MP, Food) during a battle so I can decide what actions to take.
11 | As a player, I want to be able to view my opponent's status (HP, MP, Food) during a battle so I can decide what actions to take.
12 | As a player, I want to be able to log in with a unique username so that my stats are not mixed up with other players' stats.
13 | As a player, I want to be able to view saved statistics from battles so that I can compare them to current stats and compete against them.
14 | As a player, I want to be able to navigate to different pages with a click so that I can easily access the game's features.
15 | As a player, I want to be able to see a nice user interface so that it is more of a pleasure to play the game.
16 | As a player, I want to have a user guide so I know how to use the game.
17 | As a database manager, I want to be able to update the scores so that the players know their scores.
18 | As a database manager, I want to be able to create usernames so that players can see their scores across games.

## Tasks
Tasks |  | Sources: https://www.mountaingoatsoftware.com/agile/scrum/sprint-backlog
Task ID | Task Name | Sprint ID | Story ID | Status | Priority Level | Expected Workload | Expected Duration | Comments
1 | User Stories | 1 |  | Completed | 1 | 1
2 | Use Case Diagram | 1 |  | Completed | 1 | 1
3 | Class Diagram | 1 |  | Completed | 2 | 1
4 | Sequence Diagram | 1 |  | Completed | 2 | 1
5 | GUI Design | 1 |  | Completed | 2 | 1
6 | Feature Backlog | 1 |  | Completed | 1 | 1
7 | Title/Mode Select Page GUI | 2 | 14,15 | Completed | 2 | 1
8 | Game Description Page GUI | 2 | 14,15 | Completed | 3 | 1
9 | Battle Page GUI | 2 | 14,15 | Completed | 1 | 3
10 | Single Player/Duel Page GUI | 2 | 14,15 | Completed | 2 | 2
11 | Player Stats Page GUI | 2 | 13,14,15 | In Progress | 1 | 2
12 | Enter Usernames Pages GUI for Load Game and New Game | 2 | 12,14,15 | Completed | 1 | 2
13 | Usernames Stored Retrieved from File | 2 | 12,18 | Completed | 1 | 2
14 | Save Current Data to File | 2 | 9 | In Progress | 2 | 1
15 | Calculate Score | 2 | 7 | Completed | 1 | 1
16 | User Vs User Mode | 2 | 1 | Completed | 1 | 2
17 | User Can Attack and Heal | 2 | 3,5 | Completed | 1 | 2
18 | HP and Food Increase/Decrease | 2 | 3,10,11 | Completed | 1 | 2
19 | Dice Roll Animation | 2 | 5,15 | Completed | 2 | 2
20 | User Guide | 2 | 16 | Completed | 1 | 1
21 | Calculate Win Percentage | 2 | 1,2,13 | Needs Integration | 2 | 1
22 | Display Score on Battle Page | 3 | 1,2,7,9,13 | In Progress | 1 | 2
23 | User Vs Computer Mode | 3 | 2 | Not Started | 3 | 3
24 | View Data/Statistics on View Statistics Page | 3 | 13 | In Progress | 1 | 2
25 | User Can Special Attack | 3 | 4,5 | Not Started | 2 | 3
26 | MP Increase/Decrease | 3 | 4,10,11 | Not Started | 2 | 2
27 | User Can Exit With Data Saved | 3 | 8,9,13 | Not Started | 2 | 3
28 | Player Name for Stats Page GUI | 3 | 12,14,15 | In Progress | 2 | 1
29 | Enter Username (For Playing Against Computer) Page GUI | 3 | 14,15 | In Progress | 2 | 1
30 | Display Result of Dice Roll and Computation | 3 | 12,14,15 | Testing | 2 | 2

## Sprints
Sprints
Sprint ID | Sprint Deadline | Sprint Description
1 | 2016-04-01 | Have user stories, use cases diagram, and documentation completed and committed to Github
2 | 2016-04-15 | Have at least half of the tasks completed, and documentation updated
3 | 2016-04-29 | Have everything completed, and documentation updated